## Sheet1
Gantt chart | time
updated 31 July
explanation of chart
red line indicates that this activity depends on another being completed
green line indicates the completion of a task that allows others to start
greyed in portion indicates percentage to completion
identify a clinical partner
obtain ethical approval from NHS to commence a trail
indentify trail volunteers/patients
obtain funding for trail PULS's
recruitment of a team of supporting professionals
measure up each trail patient/volunteer
manufacture bespoke trail PULS's
distribute trail PULS's to patients
commence clinical trail
evaluate results
evaluation of NHS's needs
obtain approval from NHS
costing of materials. manufacture, warehousing & distribution
submit to the NHS a quotation
obtain an initial firm order from the NHS
find and identify a financier
obtain funding for manufacture
manufacturing of initial order
supply of units to the NHS
fulfil initial NHS order